## List
[10 empty] | Date: | 2026-04-20
№ | Type | SOW | Subject | Main arrangements | Assigned to | Start date | Deadline | Priority | Customer status | Status | Comment | Request raised by | Request approved by
1 | New release | Rebates / Admin Fee | Medline Item-Commodity | Check web scrapping for Medline | Product Engineering | 2024-10-08 | tbc |  |  | On Hold
2 | New release | Discounts | Medline / Medtornic - match contract items to spend items to validate price applied | Mapping to spend descriptions in progress. Categorization close to completion; next - lineage to spend (430 records completed) | Dr.Gen | 2024-11-05 | 2024-12-12 |  |  | On Hold
3 | Feedback | Payment Terms | Iteration-III Payment Terms (days and text) | Feedback provided 21/01 | Kristina | 2024-12-16 | 2025-01-21 |  |  | Completed
4 | Feedback | Invoice Anomalies | Duplicate Payments: Iteration-III (main model) | run on 2021-2023 combined.feedback provided 13/01 | Daria | 2025-01-13 | 2025-01-13 |  |  | Completed
5 | Feedback | Invoice Anomalies | Payment Anomalies Iteration-II (anomalies in amounts) | feedback provided 17/01 | Daria | 2025-01-13 |  |  |  | Completed
6 | Feedback | Invoice Anomalies | Payment Terms Anomaly Iteration-II (anomalies in payment after due date) |  | Semen | 2025-01-13 | tbc |  |  | On Hold
7 | Feedback | Portugal | Categorization iteration-I | pharm, med equipment & IT feedback provided | Kristina | 2025-01-13 | 2025-01-27 |  |  | Completed
8 | Feedback | Portugal | SLU assignment | feedback provided 28/01 | Daria | 2025-01-13 | 2025-01-29 |  |  | Completed
9 | Feedback | Portugal | SLU assignment | prioritize suggestions for development | Dr.Gen | 2025-01-29 | 2025-03-20 |  |  | On Hold
10 | Feedback | Anomalies | 2021-2023 output | submit validation stats | Kristina | 2025-01-22 | 2025-03-06 | 2 |  | Completed
11 | Feedback | Anomalies | 2020 Fuzzy Output | 98% reviewed; transaction >$1.5k investigated | Daria | 2025-02-20 |  | 1 |  | Completed
12 | Feedback | Anomalies | 2020 ML1, ML2, Rules | 98% reviewed; transaction >$1.5k investigated | Daria | 2025-02-20 |  |  |  | Completed
13 | Feedback | Anomalies | 2024 Fuzzy Output |  | Daria | 2025-02-20 |  | 1 |  | Completed
14 | Feedback | Anomalies | 2024 ML1, ML2, Rules | submit validation stats | Daria, Kristina |  | 2025-03-10 | 1 |  | Completed
15 | Feedback | Anomalies | 2024 Vendor Dedup |  |  | 2025-02-25 |  |  |  | Completed
16 | Feedback | Vendor Dedup | Vendor Master List Sync | 2020, 2024 deduping valdation complete. Vineet to share the output (~300 vendors mismatch) | Vineet | 2025-02-20 | 2025-03-06 |  |  | Completed
17 | Feedback | Vendor Dedup | Vendor Master List Sync | validate if changes are rquired | Daria | 2025-03-06 | 2025-03-18 |  |  | Completed
18 | Feedback | Anomalies | Iteration-II output | reduce fall positives: remove lines match (fixed), monthly recurring payments (ok - have a flag now). Increase true positives: same check number scenario (output received for fuzzy); match invoice even with different number of line items based on total amount (ok - have a split invoices model now) | Product Engineering | 2025-03-05 | next execution |  |  | Completed
19 | Feedback | Anomalies | Submit new confirmed instances that were not detected by algorithms | daily | Sveta |  | daily |  |  | Completed
20 | Feedback | Anomalies | Split record algorithm review |  | Daria | 2025-03-12 | 2025-03-13 |  |  | Completed
21 | Compliance |  | 508 accessibility | [6 empty] | On Hold
22 | Feedback | Anomalies | 2021-2022-2023 split invoices |  | Semen |  | 2025-03-19 |  |  | Completed
23 | Feedback | Vendor Dedup | Vendor Master List Sync | Process Vendor Dedup Changes | Vineet | 2025-03-18 | tbc |  |  | Completed
27 | Feedback | Vendor Dedup | Validate dedup changes, see if any inconsistencies still there |  | Daria | 2025-04-01 | 2025-04-09 |  |  | Completed
24 | Feedback | Anomalies | 2021-2022-2023 split invoices |  | Daria | 2025-03-19 | 2025-03-24 |  |  | Completed
25 | Feedback | Anomalies | Confirmed Anomalies Categorization |  | Bhagya | 2025-03-20 | tbc |  |  | On Hold
26 | Feedback | Anomalies | Fuzzy across years |  | Vineet |  | tbc |  |  | Completed
28 | Feedback | Anomalies | Fuzzy across years | Feback on new flags | Kristina / Daria |  | 2025-04-09 |  |  | Completed
29 | Feedback | Anomalies | Split Multiline |  | Daria |  | 2025-04-01 |  |  | Completed
34 | Feedback | Anomalies | Split Multiline Updated output |  | Daria | 2025-04-02 | 2025-04-03 |  |  | Completed
30 | Feedback | Anomalies | Same invoice, different supplier |  | Daria |  | 2025-04-01 |  |  | Completed
31 | Feedback | Anomalies-2 | Abnormal Payment Amounts 12-sigma |  |  | 2025-04-01 | tbc |  |  | On Hold
32 | Feedback | Anomalies-2 | Late/Early Payment Anomaly |  |  | 2025-04-01 | tbc |  |  | On Hold
33 | Feedback | Anomalies-2 | QnI Anomaly |  |  | 2025-04-01 | tbc |  |  | On Hold
34 | Feedback | Vendor Dedup | Vendor Deduping | Update db | Vineet | 2025-04-08 | tbc |  |  | Completed
36 | New Release | Rebates | Vendor Names for Meditract Contracts |  | Bhagya |  |  |  |  | Completed
37 | Feedback | Rebates | Vendor Names for Meditract Contracts | Dedup check | Daria/Kristina |  | 2025-04-22 |  |  | Completed
38 | Feedback | Anomalies | AnomalyHunt Engagement: Observations for Discussion | Feedback incorporated, shared with the client | Daria |  | 2025-04-18 |  |  | Completed
35 | Feedback | Anomalies | Flags - Iteration 2 | will be provided for validation, same dataset | Bhagya | 2025-04-09 | 2025-05-22 |  |  | Completed
39 | Feedback | Rebates | Vendor Names for Meditract Contracts | Check feedback | Bhagya | 2025-04-22 | 2025-04-24 |  |  | Completed
40 | Feedback | Dedup | Across all alias names | received | Bhagya |  | 2025-09-08 |  |  | Completed
78 | Project | Chicago IT | IT Categorization Validation - Chicago/FTI | top items validation: 2024-25 - done and shared, other years to provide | Sveta / Hunter |  | wip | Delayed until 2026 | This would be to allow our consulting partner FTI to assess Chicago for a IT Savings Program | On Hold | Delayed until 2026
41 | Research | Rebates / Admin Fee | Catalogues with MPNs |  | Daria |  | tbc |  |  | On Hold
42 | Feedback | Delaware Vendor Dedup feedback | AP and PO deduping |  | Sveta |  | 2025-05-23 |  |  | Completed
43 | Feedback | Admin Fee | AP to PO integration |  | Daria | 2025-05-23 | 2025-05-27 |  |  | Completed
44 | Feedback | Anomalies | Flags - Iteration 3 | Updated flag received + comments | Kristina | 2025-06-10 | 2025-06-11 |  |  | Completed
45 | Feedback | Dedup | Deduping Amin Fee |  | Sveta |  | 2025-05-30 |  |  | Completed
46 | Feedback | Dedup | Deduping PO Manufacturer | 1K new records; at final review stage | Sveta / Daria | 2025-06-02 | 2025-06-22 |  |  | Completed
47 | Feedback | Admin Fee | PO and AP integrated file | updated output received | Daria | 2025-06-04 | 2025-06-10 |  |  | Completed
48 | Feedback | Anomalies | Re-run 2025 with Flags - Iteration 3 logics | fuzzy reversal flag question | Vineet | 2025-06-17 | 2025-06-17 |  |  | Completed
49 | Feedback | Anomalies | Feedback on anomalies | fuzzy output reviewed; feedback will be shared today | Kristina | 2025-06-17 | 2025-06-20 |  |  | Completed
50 | Feedback | Admin Fee | AP to PO lineage | rulebased part received - reviewed, ML part in progress | Bhagya | 2025-06-17 | tbc | Priority, working through legal with CC so slight delay in the expected delivery time | This is presented to Premier (GPO) on behalf of Delaware to prove underpaid fees and recoup admin fees. | On Hold
76 | Feedback | Admin Fee | PP-LA-524 Roche Diagnostics contract AP to PO lineage | rulebased part received - to review | Daria |  | 2025-07-18 |  |  | Completed
51 | Feedback | Admin Fee | PP-NS-1600 AP-PO-Distributor Report Integration | provide feedback | Daria | 2025-06-20 | tbc |  |  | Completed
51 | Feedback | Admin Fee | PO-AP lineage algorighm | Latest feedback (29/10/2025) to be implemented -- adjust output files on contract effective dates + improve PO part. | Vineet | 29/10/2025 | awaitng feedback on item master 1/29/2025 | Priority, working through legal with CC so slight delay in the expected delivery time | This is for the recovery of admin fees from Premier | Completed | Item master is under review to implememt effective dates adjustment
107 | Feedback | Admin Fee | PO-AP lineage algorighm | Delivery 4: 20 new + 2 old contracts | Vineet | 2025-09-04 | 2025-09-09 |  |  | Completed
52 | Feedback | Admin Fee | Novus Access | Item Master and PO was downloaded, looks not complete |  |  | tbc |  |  | Completed
53 | Feedback | Dedup | 400k dedup file | provide file | Vineet | 2025-06-26 | 2025-06-26 |  |  | Completed
54 | Feedback | Dedup | Chicago Deduping 2020 |  | Daria | 2025-06-26 | tbc |  |  | Completed
55 | Feedback | Dedup | Chicago Deduping 2021 |  | Daria | 2025-06-27 | tbc |  |  | Completed
56 | Feedback | Dedup | Chicago Deduping 2022 |  | Daria | 2025-06-30 | tbc |  |  | Completed
57 | Feedback | Dedup | Chicago Deduping 2023 |  | Daria | 2025-07-01 | tbc |  |  | Completed
58 | Feedback | Dedup | Chicago Deduping 2024 |  | Daria | 2025-07-02 | 2025-07-01 |  |  | Completed
59 | Feedback | Dedup | Chicago Deduping 2025 |  | Daria | 2025-07-03 | 2025-07-01 |  |  | Completed
60 | Feedback | Anomalies | 2020-2025 Chicago files with seq no |  | Vineet | 2025-06-24 | 2025-06-24 |  |  | Completed
61 | Feedback | Anomalies | Algorithms 2020 | provide file | Vineet |  | tbc |  |  | Completed
62 | Feedback | Anomalies | Algorithms 2021 | provide file | Vineet | 2025-06-30 | 2025-07-01 |  |  | Completed
63 | Feedback | Anomalies | Algorithms 2022 | received | Vineet | 2025-07-01 | tbc |  |  | Completed
64 | Feedback | Anomalies | Algorithms 2023 | ML 1 output to be provided | Vineet | 2025-07-01 | tbc |  |  | Completed
65 | Feedback | Anomalies | Algorithms 2024 | received | Vineet | 2025-07-01 | tbc |  |  | Completed
66 | Feedback | Anomalies | Algorithms 2025 | received | Vineet | 2025-07-01 | tbc |  |  | Completed
67 | Feedback |  | 6317 platform access |  |  |  | tbc |  |  | Completed
68 | Project | IT | Chicago IT Categorization | Chicago IT Suppliers and VAR flags file shared | Bhagya | 30/06/2025 | 2025-07-04 |  |  | Completed
69 | Project | IT | Chicago IT Suppliers and VAR flags | file shared | Hunter | 2025-07-01 | 2025-07-02 |  |  | Completed
70 | Project | WCI | Chicago Deduping vs 400K |  | Daria | 2025-07-01 | 2025-07-09 |  |  | Completed
71 | Feedback | Dedup | UCI Deduping | file received | Vineet |  | 2025-07-03 |  |  | Completed
72 | Feedback | Dedup | UCI Deduping | dedup file feedback | Kristina | 2025-07-03 | 2025-07-04 |  |  | Completed
73 | Project | Anomalies | Chicago - Incorporating reversals Data |  | Vineet |  | 2025-07-15 |  |  | Completed
77 | Project | Anomalies | Chicago - Incorporating void/cancel flags | finish cancel flag | Vineet |  | 2025-07-15 |  |  | Completed
74 | Project | WCI | Chicago Payment Terms Benchmarks |  | Daria |  | 2025-07-11 |  |  | Completed
74 | Project | IT | New Line Descriptions Embedding into IT Categorization | very few long descriptions, decided not to proceed now | Bhagya | 2025-07-08 | tbc |  |  | On Hold
75 | Project | IT | Chicago IT Categorization | share the feedback on Chicago IT Suppliers and VAR flags | tbc | 2025-07-08 | 15/7/2025 |  |  | Completed
76 | Feedback | Anomalies | Algorithms 2020-25 | to be shared with new void/cancel/reversal flags | Vineet | 2025-07-10 | 16/7/2025 |  |  | Completed
77 | Project | WCI | Chicago Dedup Header File | share system output once company vs person name is segregated | Vineet |  | 18/7/2025 |  |  | Completed
79 | Feedback | Admin Fee | PO-AP lineage 21 contracts | feedback | Daria |  | 2025-07-25 |  |  | Completed
80 | Feedback | Anomalies | Header File Anomalies 2020-25 | feedback | Kristina | 2025-07-23 |  |  |  | Completed
81 | Feedback | Delaware Anomalies | Delaware Rerun: incremental historical + 2 months 2025 (before 20th) | 2024-2025 30k non-verified transactions identified | Vineet | 2025-07-24 | 2025-08-15 |  |  | Completed
82 | Project | Admin Fee | PO and Admin Fee 2021-22 | data quality issues: try to incorporate into estimations for internal use | Daria | 2025-07-25 | wip |  |  | On Hold | Awaiting new data
90 | Feedback | Admin Fee | PO-AP lineage algorighm | incorporate feedback, new list of 20 contracts passed to process (received on 8/5/2025) | Vineet | 2025-07-25 | tbc |  |  | Completed
83 | Project | IT | IT Benchmarking data | all yeard provided | Vineet | 2025-07-29 | tbc |  |  | Completed
79 | Project | WCI | Chicago Dedup - Header File (8th) | share feedback on system output + dedup Master Vendor db | Hunter / Daria | 18/7/2025 | tbc |  |  | Completed
84 | Project | WCI | Chicago Payment terms benchmaring - Header file (8th) | tentative on dedup | Daria | 2025-07-29 | tbc |  |  | On Hold | Client: on hold till 2025
85 | Project | Translation | Trasnslation services | suppliers list shared | Daria | 2025-07-29 | 2025-07-30 |  |  | Completed
86 | Project | Legal | Legal services | suppliers list shared | Daria | 2025-07-29 | 2025-07-31 |  |  | Completed
87 | Project | WCI | Data preparation for EY | Source files, reports, testing | Hunter | 2025-07-29 | tbc |  |  | Completed
88 | Feedback | Anomalies | UCI Anomalies | provide feedback | Kristina | 2025-07-28 | 2025-07-31 |  |  | Completed
89 | Feedback | Dedup | UCI Deduping v2 | dedup file feedback | Kristina | 2025-07-31 | 2025-08-01 |  |  | Completed
90 | Project | Savings | Chicago Savings | provide simplified format 2 requested (provided 8/6/2025) | Vineet | 2025-08-04 | tbc |  |  | Completed
92 | Project | Anomalies | New_match_record_number to a Chicago_2020 file | add a New_match_record_number to the Chicago_2020 file to complete the training dataset | Vineet | 18/08 | 18/08 |  |  | Completed
93 | Feedback | Anomalies | Full header file | provide Header file | Vineet | 14/08 | 18/08 |  |  | Completed
91 | Feedback | Anomalies | Priorities Automation | review priority rules. Call done 14/08. K shared summary 14/08. K provided dataset 18/08. Call done 18/08. 1LetterAway fixes P1.P2. Fix identical inv numbers scenario. Substitution of letters to Numbers (was implemented but needs fix). To update considering person/company supplier type. | Semen/Kristina | 2025-07-28 | tbc | As we get more clients the lines for validation will take longer and improvement here would be high priority. | This will be used to deliver to all clients the initial AnomalyHunt offering. | Completed
94 | Project | Anomalies Chicago | Check anomalies with identified PDFs | checked all cases with matched pdfs | Kristina | 2025-08-21 | wip | High Priority, these will be used by the BA team to validate anomalies and are directly linked to near term revenue. | These will confirm anomalies and will be passed on to the client AP team. | Completed
93 | Project | IT | IT categorization: UCI |  | Vineet |  | 2025-08-06 |  |  | Completed
94 | Project | IT | IT categorization: Rush |  | Vineet |  | 2025-08-06 |  |  | Completed
95 | Project | WCI | UCI Dedup | dedup feedback submitted for processing | Vineet |  | tbc |  |  | Completed
97 | Project | Savings | UCI Savings | with format 2 output | Vineet |  |  |  |  | Completed
98 | Project | Savings | Delaware Savings | with format 2 output | Vineet |  |  |  |  | Completed
99 | Project | IT | Chicago IT - expanding categorization to all IT Suppliers | requires file 1 with mapping key | Bhagya & Vineet |  | tbc | Delayed until 2026 | This would be to allow our consulting partner FTI to assess Chicago for a IT Savings Program | On Hold
100 | Project | Savings | Irvine IT Savings Validation | requires file 1 with mapping key | Sveta |  | tbc | Awaiting complete 5 years data from UCI, we expect this will be a complete re-run | This would be to allow our consulting partner EY to assess UCI for general and specifically an IT Savings Program | On Hold
101 | Project | Savings | Delaware IT Savings Validation | received | Sveta |  | 2025-09-02 | Client Meeting 2nd September | This would be delivered direct to the client, insights and support. | Completed
102 | Project | Price comliance - Tariffs | Price change on PO file | held on 9/4/2025 | Sveta/Vineet |  | tbc | Yes but delayed 2 months (potentially - pushing for faster start) | This would be delivered direct to the client, insights and support. | Completed
103 | Project | Admin Fee | Next contracts processing | 3rd delivery - 22 contracts received (20 incremental) | Vineet |  | tbc | Priority, working through legal with CC so slight delay in the expected delivery time | This is presented to Premier (GPO) on behalf of Delaware to prove underpaid fees and recoup admin fees. | Completed
104 | Project | Anomalies | Chicago | header file - any other output for validation? | Vineet |  |  |  |  | Completed
105 | Feedback | Delaware Anomalies | Delaware Rerun: incremental 2024-2025 | new data received | Vineet |  | 2025-09-08 | Priority, expected September Start. even with potential duplicated work this is the fastest likely route to near term revenue. | These will confirm anomalies and will be passed on to the client AP team. | Completed
106 | Feedback | Chicago Anomalies | Anomalies on header file | header file - any other output for validation? | Kristina | 2025-08-18 |  |  |  | Completed
106 | Feedback | Admin Fee | Contract effective dates consideration | formulate requirements based on GPO feedback. Shared 9/2/2025 in the feedback file | Daria |  | 2025-02-09 | Priority, working through legal with CC so slight delay in the expected delivery time | This is for the calculation of admin fees to present for recovery. | Completed
108 | Feedback | Delaware Anomalies | Delaware Rerun: incremental 2024 | output received- checking | Kristina | 2025-09-08 | tbc | 2024 check is a priority; 2025 we've checked 7 months new data | This is to close out the historic portion of the engagement as we transition to the agreed continuous management for CC | On Hold
109 | Feedback | Delaware Anomalies | Delaware 2025 7 months | check complete >$1,000 | Kristina | 2025-09-09 | 2025-09-12 | priority for BA | This is to close out the historic portion of the engagement as we transition to the agreed continuous management for CC | Completed
109 | Project | Irvine SOW | Rubrik benchmark data export (t0004); check dates (eg Rush not provide for 2023-2025) | email with details sent | Vineet | 2025-09-10 | 2025-09-11 | priority as per client need | This is done as a proof of concept for the end client to build trust in the technology and hunterAI as a partner. It justifies data collection which then sets up additional future engagements | Completed
110 | Feedback | Anomalies Chicago | Chicago Anomaly: match with PDFs model | Review the model from Bhagya. Feedback shared | Kristina | 2025-08-28 | 2025-09-19 |  |  | Completed
111 | Project | Delaware Anomalies | New system output for all years all algorithms with priorities | incremental duplicates + add all captured reversed transactions into PowerBI reporting stats | Vineet |  |  | priority for Delaware delivery monthly, 10/15/2025 | This is to confirm maximum anomalies have been identified for recovery and revenue drive | Completed
112 | Feedback | Dedup | Across all alias names 400k. Iteration 1 | received. will share feedback in iterations | Kristina / Hunter / Daria | 2025-09-08 | 2025-11-01 | ongoing priority | This is done to facilitate future benchmarking as we continue to bring in new clients who want this deliverable | Completed
113 | Feedback | Admin Fee | PO-AP lineage algorigthm (new 22 contracts) | provide feedback. Task In progress | Daria |  | wip | priority as per project need | This is to help drive the admin fee program, identifying and recovering underpaid money to CC as the end client | Completed
114 | Project | Anomalies | Investegate the problem with the New Match Record Number | Review the feedback: case 1 and case are accepted, case 2 requires investigation https://gpohealthcom.sharepoint.com/sites/BusinessAnalytics/_layouts/15/doc.aspx?sourcedoc={adc221fb-9f95-4ad2-a249-487443a12801}&action=edit | Bhagya & Vineet | 2025-09-12 |  | Not a priority |  | On Hold
115 | Project | Anomalies | Fix the Imact Flag and Confirmed Spend colums | new execution received - K to review. Review the feedback https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?CID=06975a12-ad8e-d024-0e03-3cfe4cab2f14&sourcedoc=%7BFE9730F4-D1BF-43CE-B39A-E861AC011E95%7D&file=Delaware%20anomaly%207%20months%202025%20feedback.docx&action=default&mobileredirect=true | Vineet | 2025-09-12 | 2025-10-06 |  |  | Completed
116 | Project | Anomalies | Implement the new reqirment for the Reversal flag | Incorporated in the latest file - to review. Review the feedback https://gpohealthcom.sharepoint.com/sites/BusinessAnalytics/_layouts/15/doc.aspx?sourcedoc={7508dede-92db-43d9-9079-520c06b4acf5}&action=edit | Kristina | 2025-09-12 | tbc |  |  | Completed
117 | Dashboard | Demo | WCI and IT demo dashboards ' reconnect to demo from prod db and upload | provided; Sveta to test | Sveta |  | 2025-09-25 | 2025-09-25 |  | Completed
118 | Project | Anomalies | Optimization of system output file (ideally before next big anomalies processing - eg Tampa) | File to be resent. ~ approximately 1 hour of setup verification comlicated due to constant scroll back and forth | Vineet | 2025-09-16 | 2025-09-30 |  |  | Completed
119 | UCI | Dedup | 2021-2025 UCI vendors feedback (vs 400k) |  | Kristina | 2025-09-16 | 2025-09-23 |  |  | Completed
120 | Project | Admin Fee | Delivery 5 processing | new 20 contracts. 19 contracts provided | Vineet | 2025-09-18 | 2025-09-19 |  |  | Completed
121 | Web Portal |  | Automation Testing |  | Rohit / Hunter / Daria |  |  |  |  | Completed
122 | UCI | Anomalies | Anomalies 2021 Orange Facility | share feedback |  | 2025-09-19 |  | not a priority - new data with check numbers + years received |  | On Hold
123 |  |  | AI Questionaire for CCHS | Submited? | Hunter/Rohit |  |  |  | For the updated contracting process some of the CCHS stakeholders are pushing | Completed
124 | Across | Anomalies | Output structure | Can keep only new match record number | Vineet |  | next execution |  |  | Completed
125 | UCI | Anomalies | Across all years | system output | Vineet |  |  |  |  | Completed
131 | UCI | Anomalies | Across all years | feedback submited | Kristina |  |  |  | This is to maximise the identified opportunity as we look to close business with UCI directly and with EY | Completed
126 | UCI | WCI | Across all years - possible? | payments terms not available | [5 empty] | Completed
129 | Across | Categorization | IT suppliers for Delaware + Rush + UCI orange |  | Sveta | 2025-09-30 |  |  |  | Completed
127 | Across | Categorization | At a class level (or at least segment) |  | Bhagya |  | 2025-10-11 |  |  | Completed
113 | Across | Dedup | Across all alias names 400k | Implementation of the DB - deadline? | Vineet/Bhagya |  | 2025-11-25 | This is needed for the working capital offerings which are going to be positioned shortly. Prioritisation here would be good from the business side. |  | Completed
128 | Delaware | Rebates, Admin fees | Update views for category managers | categorization for UCI presented 10/22/25 - 356 suppliers with Pharma spend shared for review | Sveta / Daria |  | After task 127 |  | The aim is to continue improving the dashboard visuals in accordance to Client requests and insights, improving the overall offering | Completed
129 | Delaware | Anomalies | Typical duplicates are not captured by the system output | check why it happens (same check numbers not considered?) -- fixed in the latest executions | Vineet | 2025-10-06 | next execution |  | This is to confirm maximum anomalies have been identified for recovery and revenue drive | Completed
130 | Portal | Portal | Loading page - log in step | add "Loading may take up to 10 mins" | Rohit |  |  |  |  | Completed
131 | Delaware | Admin Fees | Delivery 8 - request | share new set of contracts for processing | Daria |  |  |  | This is for the recovery of admin fees from Premier | Completed
132 | Delaware | Admin fees | Portal set up for Premier | for weekly delivery - new customer ID needed | Rohit |  |  |  |  | On Hold
132 | Portal |  | Database loading message | After login, "0" in Dashboard section instead of report buttons . Completed; test of message disappearing done | Rohit | 2025-10-21 |  |  |  | Completed
133 | Delaware | Rebates, Admin fees | Update views for category managers | Test vendor approach (level 1, level 2, level 3) | Bhagya |  | 2025-11-25 | We will be positioning this in 2026 to more clients and by Jan we will want to have these ready to deliver |  | Completed | Level 1,2 are completed, level 3 in progress
129 | Delaware | Admin Fee | 2021-22 AP spend estimation for PP-NS-1445 | based on MPNs and descriptions in PO 2023-25. Confirm with D | Vineet | 2025-10-23 |  |  |  | Completed
130 | Delaware | Anomalies | Algos and Fuzzy historical | to review. Sveta shared manual cases to check why not captured | Kristina / Daria |  |  |  |  | Completed
131 | Across | Across | Client Upload Notifiction | To not miss anything - clients do not always notify | Rohit |  |  |  |  | Completed
132 | Delaware | Dedup | Vendor dedup aug-sep 2025 | Proceed 2 months | [5 empty] | Completed
132 | Delaware | Dedup | Vendor dedup aug-oct 2025 | Add 3 months to the library and provide feedback | Kristina |  | 2025-11-13 |  |  | Completed
132 | Delaware | Admin Fee/Price variation | Item library | Create item library with MPN, description and contracts for mapping AP and PO data -- BA team shared the suggested structure. To be shared by Vineet? Apply feedback | Vineet |  | 2025-12-02 | after contract library review |  | Completed
133 | Delaware | Anomalies | Algo and fuzzy output with Oct data |  | Kristina / Daria | 2025-11-13 | 2025-11-17 |  |  | Completed
134 | Across |  | Files in Input - review |  | Kristina / Daria |  |  |  |  | Completed
135 | Chicago | Anomalies | Reversals matched with duplicates |  | Vineet |  |  |  |  | Completed
132 | Delaware | Admin Fee/Price variation | Item library | Review: Create item library with MPN, description and contracts for mapping AP and PO data -- BA team shared the suggested structure. To be shared by Vineet? | Daria |  | 2025-12-18 |  |  | Completed
136 | Delaware | Admin Fee/Price variation | Explore Item Master | new data received | Daria / Hunter | 2025-11-18 | 2025-12-10 |  |  | On Hold
137 | Delaware | Top Services | Exploratory Data Request | Select the sample invoices from the target vendors and confirm alignment with CCHS Owner (Rich) | Hunter | 2025-11-17 | 2025-11-19 | Import to check the attributes of the services and establish the total data request for the program that will transition to OCR. |  | Completed
138 | Across | Internal | File Clean Up | Clean up input folders and change the report source files.Ascertain which files can be kept within the hunterAI data storage policy. Communicate with Rohit the outcome. Check sharepoint, aws | Kristina / Daria / Hunter | 2025-11-12 | 2025-11-28 |  |  | Completed |  | Rohit
139 | Across | Categorization | UNSPSC mapping on client data | Requires feedback on the accuracy of the spend categorization, to then be applied as slicers for Top Services. Updated file received | Bhagya | 2025-11-26 | 2025-12-12 | By deadline to have a sense check of the top areas of categorization |  | On Hold
140 | Across | AWS Transfers | Secure File Transfer | We need timeline for the transfers, we have work dependant on multiple transfers. | Kristina / Daria / Hunter | 2025-11-25 |  | High Priority, please give us a timeline and asap transfer for our requests |  | Completed
141 | Delaware | Top Services | Line item description duplication | $500k in services duplication to check themselves, and whether they have already been delivered to Client | Hunter | 2025-11-20 | 2025-11-28 | Medium Priority |  | Completed
142 | Delaware | Admin Fee | Contract Master | provide feedback | Daria | 2025-11-25 | 2025-11-27 |  |  | Completed
143 | Delaware | Anomalies | Algorithms review | feedback implemented | Kristina |  | 2025-12-08 |  |  | Completed | Book Meetin12th Dec
153 | Delaware | Admin Fee/Price variation | Item library | v2 library shared | Vineet | 2025-12-18 |  |  |  | Completed
153 | Delaware | Admin Fee/Price variation | Item library | Provide Feedback for v2 | Daria | 2025-01-15 | 2025-01-29 |  |  | Completed
163 | Delaware | Admin Fee/Price variation | Item library | Check new output provided -- all feedback implemented? | Daria | 2026-02-04 | 2026-02-09 |  |  | Completed
144 | Delaware | Anomalies | Reversal flag | feedback implementation. Case 1 | Vineet |  | 2026-01-16 |  |  | Completed | Meeting booked, Vineet Ownership
| Delaware | Anomalies | Reversal flag | Provide additional feedback | Kristina |  | 2026-01-14 |  |  | Completed
143 | Delaware | Top Services | PDFs received/Additional Chicago OCR | Staffing provided 1/22. F&b, legal, consulting - next feedback iteration | Hunter/Daria |  | 2026-02-05 |  |  | Completed | Header File reviewed. Detailed File in Progress
144 | Delaware | Top Services | PDFs received | to explore | Daria / Hunter | 2025-11-27 | 2025-12-08 |  |  | Completed | File provided to Bhagya for review
144 | Chicago | Anomalies | Reversals | During the investigation of reversals, it was found that we can currently map only 9M of negative spend to positive transactions out of 223M. Expecting the file from Vineet on 12/4/2025 | Kristina/Vineet | 2025-12-04 | 2025-12-05 |  |  | Completed | oustanding 80M? Further questions to ask of client (Desiree)
145 | Delaware | All | AI Security Questions | Need scheduling confirmation from the Dev team on if we can make the meeting slots work. | Hunter/Doc/Rohit | 2025-12-04 |  | High Priority to get this booked, it's holding up contracting |  | Completed
146 | Across | Anomalies | Anomalies algoritm | Schedule a meeting to discuss model for catching simmiliar to aproved invoices | Kristina/Semen |  |  |  |  | Completed
144 | Delaware | Top Services | PDFs received | Update from Bhagya | Bhagya |  | 2026-01-30 |  |  | Completed
164 | Delaware | Top Services | PDFs received/Additional Chicago OCR | Staffing iteration 2 OCR -- to review | Daria | 2026-02-03 | 2026-02-11 |  |  | Completed
164 | Delaware | Top Services | CCHS Invoices OCR | Staffing iteration 3 OCR -- implement critical changes, priority now. Proceeding new client data | Bhagya | 2026-02-12 | Amergis 2/27/26 | 1 | Data is expected soon | Completed
164 | Delaware | Top Services | CCHS Invoices OCR | Staffing iteration 3 OCR -- implement critical changes, priority now. Amergis feedback has been given, BA team awaiting feedback on CHG and Weatherby to be received | BA team | 2026-02-12 | Republic waste 3/5/2026. CHG, weatherby 3/12/2026 | 1 |  | Completed
148 | Across | Dedup | Dedup | Discuss the possibility of involving the dev team in the deduplication review. | [5 empty] | Completed
149 | Across | Dedup | Dedup | Deduplication review: 2000 rows. This interation is completed from BA side | Kristina/Dev team |  | 2025-12-25 |  |  | Completed | Can we have Dev team assistance?
150 | Across | Portal | Portal Formatting | When uploading the report to the portal, formatting issues occur. | Kristina / Babu |  | 2025-12-16 |  |  | Completed | Problem from PBI
147 | Delaware | Anomalies |  | Check Delaware | Daria / Kristina |  | 2025-12-11 |  |  | Completed
149 | Across | Dedup | Dedup | Implement the feedback | Dev team |  | TBC |  |  | Completed
150 | Across | Dedup | Dedup | Check the feedback Implementation | Kristina |  | 2026-01-23 |  |  | Completed
139 | Across | Categorization | UNSPSC mapping on client data | Requires feedback on the accuracy of the spend categorization, to then be applied as slicers for Top Services. Updated file received. To have a call with Bhagya. Dev team will check and share the results with BA team | Dev Team Split | 2025-11-26 | TBC |  |  | Completed
140 | Across | Categorization | UNSPSC mapping on client data | Provide feedback/Categorization. Feedback provided - to schedule a call | Kristina |  | 2026-01-23 |  |  | Completed
151 | Across | Portal testing | Portal testing | BA team tested and provided feedback 1/14/2025 | BA team | 2025-12-15 | 2026-01-14 |  |  | Completed
140 | Umass | Product Categorization | UNSPSC mapping on client data | Implement the feedback, start iteration 2. | Bhagya |  |  | 2 |  | Completed | On hold
151 | Across | Portal testing | Portal testing | Implement the feedback. For SAML requires several actions from the client side - Rohit will provide an update | Rohit | 2025-12-15 | 2026-01-28 |  |  | Completed
152 | Delaware | Top Services | Critical Fields | BA team shared critical fields from documents -- to review if they can be OCRed | Bhagya | 2025-12-11 | 2026-01-16 |  |  | Completed
154 |  | Anomalies | Filtration Model | shows similar cases to what was confirmed -- Share output | Semen |  |  |  |  | Completed
154 | Across | Across | Competition data pull (requested by S) | completed 1/15/2025 - both parts | Vineet | 2026-01-06 | 2026-01-16 |  |  | Completed
155 | Across | Across | Competition data pull (requested by S) | Initial Feedback provided | Sveta |  | 2026-01-27 |  |  | Completed
154 | Delaware | Anomalies | December data |  | Vineet |  | 2026-01-14 |  |  | Completed
155 | UMASS | Categorization | Data categorization UMASS | all source fields + categorization is requiered. IT is provided | Bhagya |  | 2026-01-21 |  |  | Completed
156 | Across | New module | To be further defined by B team. Dashboard: new vendors in anomalies - associated spend; commodity it fits in; product purchased; alternative suppliers they could have used instead of recreating new vendor. Month upon month | clients believe that they add a new vendor as they can't source from an existing. Active vs non-active suppliers. 12 months active; 18 months non-active vendors. Clarifications are needed | Vineet / Kristina | TBC |  |  |  | On hold
157 | Across | Anomalies | View on the processing time: development + BA | as of now: 2 days processing. received from the client ---> published to client. Upload times input required to complete (email sent on thursday) | Rohit/ Babu |  | 2025-01-27 |  |  | Completed
158 | Across | Categorization | Validation | Iteration 1 in checked | Kristina |  | 2026-01-29 |  |  | Completed
159 | Across | Vendor Categorization | Validation | Pilot the new metodology and share the date for 10 suppliers. Feedback shared, expecting the output. First step output is important for Primary offering ! | Bhagya |  |  | 2 |  | Not completed | After dedup agent. Now categorization based only on UNSPSC
159 | Delaware/Chicago | Anomalies | Reprocessing the full Anomalies datasets | After anomalies developments implementation | Vineet |  | Delaware Completed, Chicago WIP 2/27/2026 header completed, Chicaho detail -received 12/3 |  |  | Completed | https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BEE408316-AFBC-462E-AFCC-5AEC0D290D15%7D&file=Anomaly_dev_feedback.docx&action=default&mobileredirect=true
159 | Delaware/Chicago | Anomalies | Reprocessing the full Anomalies datasets | Line level gap in flags was identified. 03-30-26 received updated fixed file from Vineet - Anastasia to check | Anastasia |  | 2026-04-01 |  |  | Completed | Any availability for booking a call with Vineet about the anomaly feedback
159 | Across | Anomalies | Filtration Model - setup weekly update | Provide description to the model | Kristina / Semen |  |  |  |  | Completed
160 |  |  | SLA for uploads | a few files pending for a long time (copy to BA input), notify for Rohit's days off (send a meeting invite to us for a day so we have visibility?) | Rohit |  |  |  |  | Completed
161 | Across | Dedup | examples for agent development |  | Kristina | 2026-02-05 | 2026-02-09 |  |  | Completed
161 |  | Maverick spend | Feedback on Vineet's specification |  | Sveta/Daria |  | 2026-02-09 |  |  | Completed
161 |  | Chicago | no notification on Chicago feedback file upload | Check portal Uploads section functionality | Rohit |  | 2026-02-05 |  |  | Completed
165 | Across |  | Portal | Portal login waiting time -- change to 5 mins. Chicago portal issues | Rohit | 2026-02-05 | 2026-02-17 |  | Requesr from the client | Completed | We checked the portal, all good 2/19/2026
166 | Umass | All | Creation of Incoming Client Account | assign Client Name:"UMass Memorial Health" AKA "Boston" a client number, and create a new data environment | Rohit | 2026-02-12 | 2026-02-16 | 1 | UMASS Data is expected soon | Completed
162 |  | Anomalies | Portal: how to adjust to be used without Excel for client inputs. Requires input for Y/N; notes; files upload | Call 3/5/2026 | Amit |  |  |  |  | Completed
167 | Umass | All | Creation of Incoming Client Account | Give confirmation for the user name. assign Client Name:"UMass Memorial Health" AKA "Boston" a client number, and create a new data environment | Hunter | 2026-02-12 | 2026-03-18 | 1 | UMASS Data is expected soon. Customer numbers? We are still expecting client emailsUMASS 6681 (t0008). Catholic health 6682 | Completed | Emails were requested
182 | Umass | All |  | Technical qustion -- to send the answer | Doc / Rohit |  |  |  |  | Completed
167 | Delaware | GPO Admin Fees | 2021-22 Gap Estimation | Process 4 contracts with the full AP 2021-24 data | Vineet | 2026-02-13 | 2026-02-17 |  |  | Completed
168 | Delaware | Anomalies | Data check Jan26 | Review the data | Daria | 2026-02-17 |  |  |  | Completed
169 | Delaware | Dedup | Dedup Jan | Provide new Dedup part | Vineet |  | 2026-02-17 |  |  | Completed
170 | Across | Dedup | Dedup across new alieses | Root cause the issue. Feedback discussion | Bhagya |  | after task 164 | 3 |  | Not completed | Change a process?On hold
171 | Delaware | Price Variation/ GPO Admin Fees | Assign MPNs to descriptions in AP | after completion of Item Master development we will need MPNs to be assigned to AP. 2023-2026. Vineet has completed for 300 contracts - based on PO; Novus Item Master & Price File - Iteration 1 Iteration 2 - with no contract | Daria |  | 2026-04-07 |  |  | Completed | WIP
172 | Delaware | Anomalies | Manual last 18 months check | Issue with blank invoices identified, one simple case missing in system output (same number + "ADJ") identified. reviewed till 5k | Kristina |  |  |  |  | Completed
173 |  | Anomalies | PowerBi reports adjustment | Replace Card (new) visuals too avoid manual fixes | BA team | 2026-02-26 |  |  |  | Completed
174 | Portal |  | Portal adjustments | Idle time -- 30 mins , refresh view | Rohit |  |  |  |  | Completed | Extended to 60 min
175 | Delaware | Top Services | Repubic Services | Complete Contract identification and extraction, and invoice line item assessment - provide to Bhagya | Sveta/Hunter |  |  |  |  | Completed
176 | Delaware | Top Services | OCR Queue Transparency | There is P1 Republic Services, where do the CHG, Weatherby, Allergan Invoice PDFs sit in this? | Doc / Bhagya |  |  |  |  | Completed | The timeline of one vendor processed per week has been given, they are being processed in the same order as listed in the Main Arrangements Cell
177 | Delaware | GPO admin Fee / Price Variance | OCR Queue Transparency | Allergan to be set as a priority - for GPO adin fee estimation and Price Variance. Allergen - closed. Weatherby & CHG requires rework - critical issues identified, feedback sent 3-27. Add timelines, readjust priorities | Bhagya |  | 2026-04-17 |  | Allergen - Babu; Weatherby & CHG - Babu | Not completed
178 | Delaware | Anomalies | Feb data | Proceed Feb data - by week of the 9th | Dev team |  |  | 3 |  | Completed
179 | Across | Data | Data Retention | Client Data retention period - can extend above 2 weeks during the active data receipt/engagement period? | Rohit |  |  |  |  | Completed | keep the current process for now
180 | Across | Anomalies | Flags logic | Vineet to validate flags logic -- to align between Dev and BA team. Reversal Flag - Done: https://gpohealthcom.sharepoint.com/:w:/s/BusinessAnalytics/IQAvn2xG2ovPT62cAi2bQF4kAQ5ZGEQ_GMdUnD5yKxPnjEM?e=FpUa0C | Vineet |  |  |  |  | Completed | lower priority as we do not expect UMASS anomalis output
181 | Inmar | All | Creation of new client Sandbox -- for Inmar Intelligence | 5/3/2026 - submitted, start date | Rohit |  |  |  |  | Completed
181 | Across | AWS clean up |  | clean up unused / processed data files (80GB now). Review of big folders in progress. Meeting on 4/9, must be completed by then. 40GB cleaned as of 4/8. Iteration 1 closed. Request to clean duplicative files | Sveta |  | 2026-04-17 |  |  | Not completed
182 | Delaware | Vendor dedup |  | processing with agentic framework | Bhagya, Vineet | 2026-03-20 | tbc |  |  | Not completed | On hold
183 | Delaware | GPO admin Fee / Price Variance | OCR Queue Transparency | Feedback: Allergan, CHG, Weaterby | Daria | 2026-03-24 | 2026-03-27 |  |  | Completed
184 | Feedback | GPO Admin Fee | 4 contracts processed for 2021-24 | AP side estimation missing big supplier . Vineet to rerun and see is the issue persists | Vineet | teams 2/26 | tbc |  |  | Not completed | Admin Fee is a Priority after UMASS, Inmar and Delaware anomalies
185 | Across |  | Valify stats |  | Vineet |  | 2026-03-24 |  |  | Completed
186 | Across |  | PowerBI IT db report | demo report; prod report - check why savings across systems is smaller than within system. Also product attributes appears to be incomplete. Still see issues as of 4/8. Sсhedule a call to locate the files | Babu, Vineet // Daria, Sveta | 2026-03-24 | 2026-04-24 | low priority, but required for demo |  | Not completed | Babu to check the version of report and confirm numbers on the landing page
187 | Delaware | GPO Admin Fee | PP-OR-2155 Allergan estimation | augment with OCR data, observations shared. GPO Admin Fees: PP-OR-2155 Refined Estimation with OCR Input: Rerun estimation using OCR instead of AP Side. confirm the timeline next week | Vineet | 2026-03-20 |  |  |  | Not completed | Admin Fee is a Priority after UMASS, Inmar and Delaware anomalies
188 | Delaware | Additional Opportunities | 2023-26 full AP data request | with all source fileds + hAI categorazation if possible. Email with details/ request shared 2/26/26. For BA team to explore potential opportunities | Vineet | 2026-02-26 |  | low priority |  | Not completed | 6 fields requirement provided
189 | Chicago | Anomalies |  | Line-level file - payment status check; void and cancel flags. BA's checking | Vineet | 2026-03-25 |  |  |  | Completed
190 | Boston |  |  | File copying : Umass data to BA input | Rohit |  |  |  |  | Completed
191 | Chicago |  |  | Access for AP team | Rohit | 2026-03-25 |  |  |  | Completed
192 | Chicago |  |  | Response to client on anomaly algorithms | Vineet | 2026-03-25 |  |  |  | Cancelled
193 | Boston |  | Vendor Dedup | received - requested to add spend | Bhagya |  | 2026-03-31 | 1 |  | Completed | BA team to provide feedback April 2nd
197 | Boston |  | Vendor Dedup | feedback | Anastasia |  | 2026-04-02 |  |  | Completed
194 | Boston |  | IT Supplier flagging | wip --see around 123 new IT suppliers. line level check is being done | Sveta, Anastasia | 2026-04-02 |  |  |  | Completed
195 | Boston | Anomalies |  | anomalies, processed AP file with seq_no, dedup(received). Data refinement in progress. Provide Supplier Error cases using deduping -- same date, descriptions, different initial names, same amount. Provide if processed (call 4/16) | Vineet |  |  |  |  | Completed
196 | Across |  |  | provide input on anomaly agent | Sveta, Daria |  | 2026-04-07 |  |  | Completed
197 | Boston |  |  | Broad item categorization, segment level | Bhagya |  | 2026-04-07 |  |  | Completed
198 | Boston |  | DPO | Vineet to look into PT availability data | Vineet |  | 2026-04-08 |  |  | Completed
196 | Boston |  | IT | IT Categorization output in db. (received -- BA to provide feedback) + files 1 (wip, to be shared 4/15?) and 2 (to be shared 4/14) not received | Bhagya |  | 2026-04-09 |  |  | Completed
199 | Inmar Intelligence |  | Anomalies | Dedup + Anomalies Output (first 2025 data, then other years, categorization is on hold now) | Vineet |  | 2026-04-15 | same as UMASS |  | Completed | will be processed after UMASS. 32k suppliers ! Dedup by early next week?
200 | Portal |  |  | portal - add report name in the tab, open all reports in new tabs. To connect with powerbi team | Rohit |  |  |  |  | Not completed
201 | Boston |  |  | WCI benchmarks to be provided | Sveta |  | 2026-04-10 |  |  | Completed
202 | Boston |  |  | Item-Segment feedback. Checked - minor issues, no feedback | Hunter |  | 2026-04-16 |  |  | Completed | sense-check
203 | Delaware | Anomalies | March Anomalies | process March anomalies (full AP, anomalies, dedup) | Vineet | 2026-04-08 | 2026-04-14 |  |  | Completed
204 | Inmar Intelligence |  | WCI benchmarks | Input expected 4/20, BA to review and provide benchmarks | BA team |  | 2026-04-21 |  |  | Not completed
205 | Inmar Intelligence |  | Anomalies | 2025 anomalies output - provide feedback | Anastasia | 2026-04-16 |  |  |  | Not completed
206 | Inmar Intelligence |  | Anomalies | vendor Dedupe - provide feedback | BA team | 2026-04-15 |  |  |  | Not completed
207 | Delaware | Anomalies | March Anomalies | Provide feedback and delivery selection | Daria |  | 2026-04-20 |  |  | Not completed
208 | Policy |  |  | ISO policy communication, meet with Hunter & Sveta | Rohit
209 | Delaware | Anomalies | Vendor Dedupe | Share dedupe Oct 2025 - now. | Vineet

## Anomalies Development
[12 empty] | Date: | 2026-04-20
№ | Type | SOW | Output file | Subject | Model | Main arrangements | Feedback Link | Registration date | Deadline | Assigned to | Priority | Status | Comment | Request raised by | Request approved by
1 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Reversal Flag | Across | Propogate the flag for the entire match (currently sometimes differet values inside a match) | Reversal flag.docx | 2025-09-12 | next execution |  |  | Completed
1 | Future improvements | Anomalies |  | Reversal Flag | Across | With the current logic, the reversal flag may result in false positive reversals, since there is no condition ensuring that one invoice can be considered a reversal of only one other invoice. Under the current approach, multiple invoices can be mapped to a single invoice. New feedback | Anomaly improovements check.docx | 2025-10-11 | 2026-02-03 | vineet | 2 | Completed | te new logic is elaborating. the scale of the issue will be calculating after receving the file with all reversals
2 | Feedback | Anomalies | 2025_aug_sep_Delaware | Reversal Flag | Across | Negative values are currently appearing in the system output without a reversal flag, while in the source file there are positive transactions for the same amount from the same vendor dated earlier.New feedback | Anomaly improovements check.docx | 2025-10-12 | 2026-02-03 | vineet | 2 | Completed
3 | Feedback | Anomalies | 2025_aug_sep_Delaware | Algoritm | Across | The issue with including invoices with different invoice amounts in the matches has become more significant. It is necessary to review the logic of the new match reversal number. |  | 2025-10-13 | 2025-11-07 |  | 1 | Completed | 10% difference, line description should be similliar. Apply to completed invoices: invoice amount&vendor&sipplier_invoice number.
3 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Incompleted invoices | Across | Exclude incomplete invoices from the dataset. Only invoices that include all records with the same vendor name, invoice amount, and supplier invoice number should be considered — similar to point 3. |  | 2025-10-28 | 2026-02-03 |  | 1 | On Hold | ? Appears to be similar to N6
4 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_2 | Incompleted invoices_reversals | Across | Solve the issue with negaive invoice amounts | https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BDD52EDEA-AF79-4C32-860E-257CE5F88EBC%7D&file=Anomalies%20improvements%20review%202.docx&action=default&mobileredirect=true | 2025-11-10 |  | vineet | 2 | On hold
4 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Lines from the same invoice are matched | Same supplier but discrepancies in invoice records | Exclude - generates many extra lines in the output |  |  | 2025-11-07 |  | 1 | Completed | invoice amount&vendor&sipplier_invoice number. Consider check number only if the sum of ext amount = invoice amount
5 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | New_matched_record_number | ML1.1, ML2, same invoice details but different check details | Multiline invoices duplicate ends up in different matches -- inside one matched record number there's only one invoice line | Case 2 https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BADC221FB-9F95-4AD2-A249-487443A12801%7D&file=New%20match%20number%20feedback.docx&action=default&mobileredirect=true |  |  |  | 3 | completed
5 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Split invoices model -- ML1.3 | ML1.3 | Many lines generated now and hard to review -- Vendor and Invoice number fields are not considered in the model. The mojority is right away not a duplicate. Suggestion: keep matches only with the same Vendor or with similar Invoice Numbers | Case 1 https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BADC221FB-9F95-4AD2-A249-487443A12801%7D&file=New%20match%20number%20feedback.docx&action=default&mobileredirect=true |  |  | semen | 2 | closed (not a priority) | During the discussion, it was agreed that incomplete invoices may exist and this is not an issue as long as all invoice lines are captured.
6 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Incomplete invoices captured | ML1.1, ML2, same invoice details but different check details | Invoice Amount in a dupicate is the same, but only several lines form multiline invoices are captured in the output. May be related to item #4? | Delaware_anomaly_feedback_2 |  | 2026-02-03 |  |  | On Hold | We observe the issue; however on hold for now
8 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Impact Flag | Across? | In a match with multiline invoices, Impact flag is only on one line | Impact flag section https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BFE9730F4-D1BF-43CE-B39A-E861AC011E95%7D&file=Delaware%20anomaly%207%20months%202025%20feedback.docx&action=default&mobileredirect=true |  | next execution |  |  | Completed
9 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Same check number scenario | Across? | Do algotightms consider same check duplicates? We manually found great duplicates that are missing in the system output -- they mainly have same check number. | Different check numbers inside the invoice section https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BA1A2B2DC-A06C-4C24-B29C-2BBD154844B0%7D&file=UCI%20data_check.docx&action=default&mobileredirect=true | 2025-07-31 |  |  | to check | Completed
7 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Cancel Flag |  | Propogate the flag for the entire match (currently sometimes differet values inside a match) |  | 2025-09-16 | next execution |  | to check | Completed | In Delaware output there are no canceled
11 | Feedback | Anomalies | 2025_all_algo_anomaly_delaware_data_1 | Date in supplier invoice number flag |  | A problem was also found in the operation of the date in supplier invoice number flag. | Date in supplier invoice number flag section https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BFE9730F4-D1BF-43CE-B39A-E861AC011E95%7D&file=Delaware%20anomaly%207%20months%202025%20feedback.docx&action=default&mobileredirect=true | 2025-09-12 | 2025-11-07 |  | 1 | Completed | Responsible: Semen
8 | Future improvements | Anomalies | UCI_anomaly | Future improvements: Date in the invoice numbers |  | The UCI data includes numerous monthly transactions, which is reflected in the changing month number in the middle of the supplier invoice number. This is also documented in the Line Description. Incorporating this factor into the model would significantly reduce verification time. | Section Future improvements: Date in the invoice numbers https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7BA1A2B2DC-A06C-4C24-B29C-2BBD154844B0%7D&file=UCI%20data_check.docx&action=default&mobileredirect=true | 2025-07-31 | next execution | Bhagya | 4
13 | Feedback | Anomalies | Chicago | Priority model |  | Current next steps: Merge the two flags into one, taking into account the increased prioritization from the priority_additional column. | https://gpohealthcom.sharepoint.com/:w:/s/BusinessAnalytics/ERb8l2E3HYhMnooY242rtUcBlUI1JbzTg6o37YtLFY5xkA?wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&wdExp=TEAMS-TREATMENT&wdhostclicktime=1759424021430&web=1 |  |  |  |  | Completed
9 | Future improvements | Anomalies | Chicago | Future improvements: White & Black box models |  | At present, the prioritization model covers 80–90% of the identified duplicates but generates a significant number of false positive results. The implementation of white-box and black-box models will improve the efficiency of the models and enhance their adaptability to other clients. K to provide input | https://gpohealthcom.sharepoint.com/:w:/s/BusinessAnalytics/ERb8l2E3HYhMnooY242rtUcBlUI1JbzTg6o37YtLFY5xkA?wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&wdExp=TEAMS-TREATMENT&wdhostclicktime=1759424021430&web=1 |  |  | Priority | 4 | On hold
10 | Future improvements | Anomalies | Chicago | Future improvements: Supplier pattern |  | The goal is to capture supplier-specific transaction patterns to more accurately detect duplicates and expand coverage to non-standard cases. | https://gpohealthcom.sharepoint.com/:w:/s/BusinessAnalytics/ERb8l2E3HYhMnooY242rtUcBlUI1JbzTg6o37YtLFY5xkA?wdOrigin=TEAMS-MAGLEV.p2p_ns.rwc&wdExp=TEAMS-TREATMENT&wdhostclicktime=1759424021430&web=1 |  |  |  | 4
16 | Feedback | Anomalies | 2025_aug_sep_Delaware | Unpaid and unreconciled invoices |  | we need to chage this to unpaid only. |  |  | 2025-11-07 |  | 1 | Completed | The same logic as VOID
11 | Feedback | Anomalies | 2025_nov_Delaware | New_matched_record_number |  | Invoices with identical invoice numbers are not catched by the algoritm | https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7B6419C5CB-5B91-4F06-A405-CB24BCD6DD69%7D&file=Delaware_anomaly_Nov2025.docx&action=default&mobileredirect=true |  | 2025-11-08 |  | 2 |  | completed
12 | Feedback | Anomalies | 2025_nov_Delaware | Date in supplier invoice number flag |  | A problem was also found in the operation of the date in supplier invoice number flag. Semen provided the feedback that solving this promplrm will overfit the model. to discuss | https://gpohealthcom.sharepoint.com/:w:/r/sites/BusinessAnalytics/_layouts/15/Doc.aspx?sourcedoc=%7B6419C5CB-5B91-4F06-A405-CB24BCD6DD69%7D&file=Delaware_anomaly_Nov2025.docx&action=default&mobileredirect=true |  |  |  | 1 | On hold | Responsible: Semen
13 | Feedback | Anomalies | 2025_nov_Delaware | Reversal group number |  | Reversals group number​. Doesnt work correctly | Reversals group number​ |  |  |  | 2 |  | Completed
14 | Feedback | Anomalies | 2025_nov_Delaware | Vendor name alies |  | Vendor name alies fiels sometimes is empty |  |  |  |  | 2 |  | completed
15 | Feedback | Anomalies | 2025_nov_Delaware | Match between lines |  | There is still an issue where different line items within the same invoice are being matched to each other. | Delaware_anomaly_feedback_2 |  |  |  | 2 | Completed
16 | Feedback | Anomalies | Across | Filtration model |  | Add source in the output
|  |  |  | Future improvements |  | seq n across invoice |  |  | 2026-02-03 |  |  | Completed

## Admin Fee Development
[11 empty] | Date: | 2026-04-20
№ | Type | SOW | Output file | Subject | Main arrangements | Feedback Link | Registration date | Deadline | Assigned to | Priority | Status | Comment | Request raised by | Request approved by
1 | Feedback | GPO Admin Fee |  | Item Master -- Contract master (contracts + effective dates) and Contract Linkage (contracts relationship) | Please refer to feedback file. Adjust output files based on contract effective dates and related contracts | Item_Master.docx | 2026-02-10 | 2026-02-17 | V | 1 | Completed | aim to close everything in the next iteraton
2 | Feedback | GPO Admin Fee |  | Item Master -- Contract MPN master and Contract MPN Map (all descriptions and MPN consolidated and linked to contracts) | Please refer to feedback file. Suggested structure in green | Item_Master.docx | 2025-12-18 | ? | V | 2
3 | Feedback | GPO Admin Fee |  | Improve PO-side estimations | Please refer to feedback file. Estimations should be based on the item list for the contract, not solely on the Contract Number column in the PO file. For PO estimation there is a big discrepancy - my understanding that the algorithm just refers to the Contract Number column in PO. Correct approach would be to create a contract product list using PP-CA-446 and PP-CA-636 in POs. And then find all related PO spend for these items -- this way we get the full picture and have a consistent approach with the AP part. | AP_PO_Integration.docx | 2025-10-29 |  | V | Can be implemented as the next step development, not critical now
4 | Feedback | GPO Admin Fee |  | Extended Amount sign logic | As discussed on Teams, this issue was fixed -- just want to make sure it’s fully incorporated into the algorithm. | email 12/26 | 2025-12-26 |  | V |  | Completed
5 | Next Steps | GPO Admin Fee |  | Reprocessing scope | After all changes are implemented and the Contract Master files are finalized, the next step will be to reprocess all previously delivered data including 2021-2022. We can start with the contracts from Deliveries 1-2, sharing the list (client Export Data folder, "Admn_Fee_Requset_to_Reprocess_12.26" dated 12/26/25) | email 12/26 | 2025-12-26 |  | V | 3 - after priorities 1 and 2 are closed
6 | Feedback | GPO Admin Fee | 4 contracts processed for 2021-24 | AP side estimation missing big supplier |  | teams 2/26 | 2026-02-26 |  |  | 1 - critical not to lose big AP chunks
7 | Feedback | GPO Admin Fee | 4 contracts processed for 2021-24 | PO side estimation is lower than in Source files |  | teams 2/26 | 2026-02-26
8

## Sheet1 (hidden)
anomaly output
seq_num | new match record no | invoice number
1 | 1 | 100
3 | 1 | 100
source data
seq_num | invoice number
1 | 100
2 | 100
3 | 100
4 | 100

## Notes (hidden)
Date | SOW | Subject | Discussed | Assigned to | Action | Deadline | Priority 1/2/3 | Status | Commentary
2023-11-23 |  | 13% DLTP items don't have hunterAI IDs | T14 instance reviewes | BA | Provide example |  |  | Closed
2023-11-23 |  | KP data | segment_flag has values 0,1,3 | Engineering | Use dev server only for segm flag |  |  | Closed
2023-11-23 |  | KP data | What is an actionable feedback? | BA | Prioritize Segments/Commodities, Provide a feedback in that way |  |  | Closed
2023-11-23 |  | Min price in savings | Comes from outlier lines | Data Science | Validate the reason for different min price for outliers in few instances |  |  | Closed
2023-11-23 |  | Methodology | To be prepared for savings | Data Science | 1. Received feedback 26/12/2023 2. 01/04/2024 feedback from Data Science was provided 3. 01/19/2024 feedback form BA team was provided 4. 01/23/2024 feedback was provided by Bhagya 5. 01/23/2024 replied by BA team Closed |  | 3 | Closed
2023-11-23 |  | File 2 aggregation | sum up facility level breakdown in export file only | BA |  |  |  | Closed
2023-11-28 |  | Item_OEM | Observations discussed | BA | 1. Accessories - ag Apple case 2. Services - Do we include and how? Eg Accenture, PWC, Cognizant |  |  | Closed
2023-11-28 |  | Vendor Deduping (Invoice vs AP vendors) | Deduping improvements and separate discussion is required | BA | BA suggested an additional check. Ready to check. 26/12/2023 BA to receive the file from Vineet 1. 01/02/2024 - BA placed a request to reveal details of the data behind the deduping list 2. 02/06/2024 refreshed data was provided 3. 02/08/2024 feedback was provided by BA team 4. Request to add the source (does it come from AP/PO/Invoice) 5. 02/19/2024 Enriched data was provided by Vineet Bhagya 02/23/2024: i have given an updated AP Invoice Vendor Dedup file to Vineet few mins back. This is for the 26 systems data. He will let you know once he updates the dimension |  |  | On hold
2023-12-11 |  | File_1_2_requirements | Required changes in the Output files (File_1, File_2) | BA | 1. Provided by Engineering Team, 2. Feedback from BA - provided 01/10/2024, 3. Vineet responded on 01/11/2024 4. 01/18/2024 Required changes are implemented and accepted. |  | 3 | On hold | Once IT_Suppliers_flag issue and OEM issue are fixed, to check data one more time
2023-12-11 |  | IT_suppliers_flag case | Verathon case - different IT_Supplier flag in Fact table and Savings Table | Engineering |  |  | 3 | Closed
2023-12-11 |  | Item_OEM into DB | Firstly on Duke data | Engineering |  |  | 1 | Closed
2023-12-11 |  | Item_OEM across 26 systems | To spread OEMs across all 26 systems | Data Science | 1. The first iteration was received from ET on 01/09/2024 - verification is in progress. 2. Feedback from BA team was provided on 01/12 about discrepancy for Duke's data. Waiting for Bhagya's answer 3. 01/22/2024 data was reuploaded, top level numbers for Duke look good 4. Feedback was provided on 01/31/2024 5. Second iteration was provided on 02/14/2024 + commodity check 6. Feedback was provided by BA team 02/16/2024 7. 21/02/2024 BA Team accepted part for IT Suppliers There are part of checked rules (for non-IT Suppliers part) which should be applied in the next iteration. Should be verified on Member1&Member3 reprocessed data |  |  | Closed
2023-12-12 |  | The list with standard reports | Compile the list with 4-5 reports which can be standard across different products | BA |  |  | 1 | Closed
2023-12-19 |  | Additional fields into flat export of uncategorized Member4 | to provide list of fields that need to be added into the flat file | BA | request from BA sent on 19/12 |  | 1 | Closed
2023-12-19 |  | PowerBI upgrade to Dec release |  |  | awaiting for the update notification from Microsoft |  |  | Closed
2024-01-09 |  | 26 systems data: blank Invoice spend and non blank Savings (Duke's example) | 26 Systems check.docx | Engineering | Null comes from the source. Blank invoice spend is still there. 1/23/2024 resolved - to check BA team 02/05/2024 - issue appears again |  | 2 | Closed
2024-01-09 |  | Zaplify security approval |  | Info Security |  |  |  | Closed
2024-01-09 |  | Zoho Account for EY |  | Info Security | to check if we can make 1 account for multiply users. Sveta and Rohit to test how that works, including masking part - one project for both internal and external Jeffrey approved 1 account cost 12 Feb - Rohit & Sveta tested | 2024-02-08 | 1 | Closed
2024-01-09 |  | Reports from Babu - provide feedback | hunterAI_product_2023 |  | BA - to provide look and feel for the first page. For demo demonstations 1/26/2024 the first page was redisgned and provided to Babu Documentation |  |  | Closed
2024-01-10 |  | Release III performance optimization |  |  | 1. Release-III file was provided on 01/14. 2. Metrics with direct connection to DB were updated + extra cards were removed (BA team). The last R-III version was provided to Dev Team (01/18/2024) 3. 01/23/2024 current version is provided by Babu for futher UI/UX enhancements |  |  | Closed
2024-01-10 |  | IT suppliers flags issue in DB Prod | It suppliers flags were changed in comparison with data provided to the client |  | 1. BA to check the list with IT Suppliers Alias which have both 1/0 IT flag 2. 01/22/2024 corrected file was provided to Vineet 3. 01/23/2024 The list of IT Suppliers is correct. Closed |  |  | Closed
2024-01-22 |  | Medical Model | Medical Model verification - Iteration 1 |  | 1. 01/18/2024 The first model for 250 commodities Feedback provided by BA team 01/25/2024 |  |  | Closed
2024-01-23 |  | Release III notes | To create Release notes (documentation) |  | 1/30/2024 Report documentation was provided |  |  | Closed
2024-01-25 |  | Analysis for Medical model | Make comparison between same IM and Predicted commodities (coverage) |  | 1. To show what is the improvement within unclassified data |  |  | Closed
2024-02-05 |  | Unclassified datasource enhancements | 1. To add 4 columns 2. To resolve NULL GL Account issue | Vineet | 02/05/2024 Vineet has provided the file with required changes There are big discrepancies for | 2024-02-06 | 1 | Closed
2024-02-06 |  | F&B_Beef_Savings_Demo | The page Price Variation by Product doesn't work Source for this report is l1_tbl; f_and_b_detail_segment4_Table Connector: L1 MySQL-Sveta | BA | To move this report to Prod - to keep only one server for demo puproses 1. 02/08/2024 Report was relocated to Prod server. Needed verification and approval from BA 2. 02/09/2024 a lot of discrepancices were founded and provided to Babu to fix 3. Fixed report was provided on 02/15/2024 4. 02/21/2024 Report was moved to Demo server 5. Verified by BA team. The report could be reuploaded to PowerBI server | 2024-02-27 |  | Closed
2024-02-06 |  | F&B_US_Foods_Sysco_Demo | F&B_US_Foods_Sysco_categorization page doesn't work Source: L4_Demo doesn't work at all | BA | To move this report to Prod - to keep only one server for demo puproses 1. 02/08/2024 Report was relocated to Prod server. Needed verification and approval from BA 2. No issues in Prod 3. Reuploading to PowerBI Service 4. 02/21/2024 Report was moved to Demo server 5. Verified by BA team. The report could be reuploaded to PowerBI server | 2024-02-27 |  | Closed
2024-02-06 |  | Clean-up |  | Info Security |  | 2024-02-09 |  | Closed
2024-02-07 |  | Duke's Invoice spend enriched by GL accounts | To add GL accounts into Invoice dataset where are no many-to-many relationships |  | 1. 02/09/2024 new file was provided by Vineet 2. AP file with Invoice Numbers is needed for verification purposes 3. 02/13/2024 feedback was provided by BA team 4. 02/19/2024 fixed data was provided by Vineet Checked, accepted |  |  | Closed
2024-02-08 |  | To upload from SQL the latest list with Invoice and AP Vendors | To upload Vendor_Name, Vendor_Name_Alias, Invoice Spend, AP SPend, IT Supplier flag, VAR_verified_flag, Vizient_Supplier_flag for 26 systems |  | Provided |  |  | Closed
2024-02-08 |  | Member1 deduping names file | To upload Vendor_Name, Vendor_Name_Alias, Invoice Spend, AP SPend, IT Supplier flag, VAR_verified_flag, Vizient_Supplier_flag for Member1 | Vineet | 1. 02/09/2024 the file is provided IT Suppliers first 2. Checked - closed To check why do we have so much AP Vendors |  |  | Closed
2024-02-08 |  | Med Model 2nd iteration validation |  | Data Science | 1. 02/08/2024 provided by Data Science 2. 02/14/2024 updated file was provided by Data Science Manufacturing code discussion - to add where it possible 3. 02/20/2014 feedback was provided by BA team IT-Suppliers list check + Commodity Check | 2024-02-29 |  | On hold
2024-02-13 |  | Standard_reports_V1 and Standard_DLTP_reports_V1 | To fix the issues with these reports, keep them on AWS and delete from PowerBI service |  | Reports were provided. Need to be verified by BA team and deleted from PowerBI Service 02/19 reports are saved on AWS. The path: PowerBI reporting/Old reports Reports were deleted from PowerBI service |  |  | Closed
2024-02-15 |  | ABG_report and Release-III to Demo server |  | BA | To move reports for Demo purposes to Demo server 2. To check reports based on 5 Systems data | 2024-02-29 |  | Closed
2024-02-16 |  | dim_tables consistency for client in case of multiple channel partner | IT_Suppliers flag: discussion in case if we have different IT_suppliers lists for different partners |  |  |  |  | Hold
2024-02-21 |  | Member 1 & Member3 GL to Invoice, New categorization, OEM to Invoice Validation | OEMs, Vendor-based approach, Medical model, AP-Invoice integration | BA | 1. 02/21/2024 provided by Vineet Verification plan: 0. Deduping 1. M&A 2. Finance views 3. OEMs 4. Savings 5. Med. model |  |  | On hold
2024-02-26 |  | London's data: deduping verification | To check the quality of deduped names | Data Science | 02/26/2024 the first deduping list was provided by Data Scientist team 02/27/2024 the feedback was provided by BA team |  |  | Closed
2024-02-26 |  | London's data: IT_suppliers list | To mark IT Suppliers | Data Science | 02/26/2024 the first deduping list was provided by Data Scientist team 02/27/2024 the feedback was provided by BA team |  |  | Closed
2024-02-26 |  | Test Web Portal | Testing efforts should focus on validating the login process, dashboard functionality, data upload capabilities, detail data sections, and Power BI reports | BA | 04/24/2024 feedback was provided by BA Team 05/10/2024 test 2.0 feedback provided by BA | 16.05.2024 to be provided by Security |  | Done
2024-02-29 |  | Legal offering | Create a technical specification for legal invoices | BA |  |  |  | Done
2024-02-29 |  | Customer feedback / call centers / contact centers | To scout data/samples/analysis types | BA | completed on May 4th |  |  | Done
2024-02-29 |  | Contracts data (samples) | To scout data/samples/analysis types | BA |  |  |  | Hold
2024-02-15 |  | Discharges summaries | To scout data/samples/analysis types | BA |  |  |  | Hold
2024-05-10 |  | Access for Michael - aws |  | Security |  |  |  | Done
2024-05-10 |  | Access for SG - Zoho and S3 |  | Security |  |  |  | Done
2024-05-16 |  | OCR legal Suppliers |  | Data Science | 05/16/2024 feedback for 4 Suppleirs was provided by BA team |  |  | Done
2024-05-16 |  | ? Check domain blocking list? | Toptal Unblock | Security & BA | BA to send a confirmation email Create a shared space to monitor and review | 2024-05-23 |  | Done
2024-05-16 |  | Future - London dedup 2021, 2022 | request PO files - BA team. Confirm completeness of PO files. Goods Received Note |  | Request passed; London confirmed data to be provided early this week |  |  | Done
2024-05-16 |  | Future - London new Legal files | BA to follow-up |  | Files received. Priority TBC |  |  | Done
2024-05-16 |  | Future - Singapore 1) additional fields into AP. 2) Examples of xml. 3) Example of pdf files for freight. | 1) Only Vendor deduping in scope as of now 2,3) Output received 5/30/2024 |  | 1) deduping ok 2) XML feedback provided 6/5/24 | 2024-05-22 |  | Done
2024-05-21 |  | London AP Deduplication Algorithm | 5/20/2024 passed to BA for testing | BA | BA; check each scenario. Vineet; explore the uncaptured confirmed instances | 2024-05-29 |  | Done
2024-05-21 |  | OCR legal Suppliers | 4 new suppliers - validation | BA |  | 2024-05-22 |  | Done
2024-05-21 |  | Test Web Portal | 5/21/2024 passed to BA for testing | BA | Feedback provided by BA 5/28/2024 Customer->SOW->Iteration BA to present to London 6/11/24 | 2024-06-03 |  | Done
2024-05-21 |  | Singapore Classification | [5 empty] | Done
2024-05-27 |  | New Legal OCR | 5/27/2024 passed to BA | BA | wip |  |  | Done
2024-05-28 |  | London: Vendor Dedup - 2021-2022 | Vineet will provide file for dedup check + new SG vendors dedup |  | BA feedback provided 5/31/2024 |  |  | Done
2024-05-28 |  | London: Duplicate Payment Identification - 2021-2022 |  |  | Scenarios 1,2 - feedback provided 6/1/2024. Next 3 sceanrios received by BA on 6/4/2024 All scenarios 2023 feedback provided 6/6/2024 | 2024-06-12 |  | Closed
2024-05-28 |  | Cleanup of old data - individuals |  |  | Backup confirmation to be provided 6/13/2024 | 2024-06-12 |  | Done
2024-05-28 |  | BA Input folder - two timelines are coming | Client Data Movement Tracker.xlsx |  | Confirmation from BA provided |  |  | Done
2024-06-04 |  | Packaging - Commodity to Packaging L2 mapping |  |  | Completed by BA 6/4/2024; will be provided on the same date | 2024-06-04 |  | Done
2024-06-11 |  | Bottomline legal requirements |  | BA | Provided 6/13/2024 | 2024-06-12 |  | Done
2024-06-11 |  | Access for London to the Web Portal |  | Security | Provided 6/11/2024 | 2024-06-11 |  | Done
2024-06-13 |  | DL Anomalies Scenarios | BA to Provide feedback | BA | Checked - WIP |  |  | Closed
2024-06-13 |  | Distance Report | BA to Provide feedback | BA | Checked |  |  | Closed
2024-06-24 |  | Sentiment analysis | BA to Provide feedback | BA | Twitter to be added. Daria & Bhagya to have a call | 2024-07-09 |  | Closed
2024-06-25 |  | Legal Invoices - Iteration II | BA to Provide feedback | BA | Feedback provided on 07/10/2024 Morgan Lewis, Bottomline Technologies are pending Explore automation opportunities: BA - describe step be step process in flagging and check reporting. Roles assignement to be manual. Roles - test chatGPT using website URLs. Google Gemini |  |  | Closed
2024-06-27 |  | Late Payment Benchmarks 61 Systems |  | BA |  |  |  | Closed
2024-07-02 |  | Home Page for London - combine Invoice Recovery, Legal, IT, Late Payment under the one report |  | BI team |  | 2024-07-03 |  | Closed
2024-07-02 |  | Blood Bank requirements |  | Data Scientist | BA Feedback provided | 2024-07-02 |  | Closed
2024-07-02 |  | Anesthesia requirements |  | Data Scientist |  | 2024-07-02 |  | Closed
2024-07-02 |  | ADA tool testing | test on 2023 vs known duplicate / output | BA | anything new we find using the tool? | 2024-07-25 |  | Closed
2024-07-02 |  | Active Data testing (excel data) | test on 2023 vs known duplicate / output | BA | anything new we find using the tool? | 2024-07-25 |  | Closed
2024-06-30 |  | Savings Table - provide fields which are not using |  |  | Columns provided on 07/11/2024. Lena to send an email. Email sent. Awaiting for test table to check R-III report with reduced savings table was checked | 2024-07-18 |  | Done
2024-07-04 |  | Blood Bank feedback |  | BA | Dr.Gen to check - codes in invoices - what we can deduce | 2024-07-11 |  | Done
2024-07-04 |  | Anesthesia feedback |  | BA | Format 1,2 accepted | 2024-07-04 |  | Closed
2024-07-04 |  | Anesthesia contracts analysis |  |  | Dr.Gen to look for benchmarking - anest. services |  |  | Done
2024-07-09 |  | Lighthouse Home page - enable in web portal | multiple sign-on requests for PowerBI | BI / Info Security | Checked by BA team | 2024-08-20 |  | Closed
2024-07-15 |  | Fuzzy logics 2021-2022 | test | BA | feedback provided 7/15/2024 new fuzzy logics output received feedback provided 7/25 | 2024-07-25 |  | Closed
2024-07-15 |  | ChatGPT in Teams fix |  | Info Security |  | 2024-07-16 |  | Closed
2024-07-16 |  | Claims Output Feedback |  | BA | new output recived 7/23 | 2024-07-26 |  | Closed
2024-07-16 |  | Premium Prediction |  |  | feedback provided 8/1 | 2024-08-01 |  | Closed
2024-07-16 |  | Sentiment Analysis | Iteration-II |  | PowerBI report prep |  |  | Closed
2024-07-18 |  | Legal: Explore automation opportunities: BA - describe step by step process in flagging and check reporting. Roles assignement to be manual. Roles - test chatGPT using website URLs. Google Gemini |  | BA |  |  |  | Hold
2024-07-30 |  | Fuzzy logics 2023 | test | BA | feedback provided 7/31 | 2024-08-02 |  | Closed
2024-08-05 |  | US Foods Format 1 OCR validation | test | BA |  | 2024-08-07 |  | Closed
2024-08-05 |  | London 2024 Anomalies: 4 priority scenarios validation | test | BA | feedback provided 8/7/24 | 2024-08-08 |  | Done
2024-08-07 |  | Payor Contracts | received 8/7/24 |  | requires Web Portal setup | 2024-08-09 |  | Done
2024-08-12 |  | London - Confirmed Duplicate payments - Categorization | received 8/12/24 | BA |  | 2024-08-14 |  | Done
2024-08-19 |  | Portal Access Issues | [5 empty] | Done
2024-08-20 |  | Vendor dedup for 2 new files ("GPO file" and Meditrack file) |  |  |  | 2024-08-22 |  | Closed
2024-08-20 |  | AP Anomalies new filter columns 2021-2022-2023 (4 scenarios) |  |  |  | 2024-08-22 |  | Closed
2024-08-29 |  | Benford Law Anomalies Test | first 2 digits completed. File to be received for check |  |  | 2024-10-04 |  | Closed
2024-08-21 |  | Sentiment Iteration II feedback |  | BA |  | 2024-08-22 |  | Closed
2024-08-27 |  | Payment clause extraction - POC | 84% accuracy |  |  |  |  | Closed
2024-08-29 | Rebates / Amin Fee | Contract Titles to UNSPSC | feedback provided; no action required |  |  | 2024-10-17 |  | Done
2024-08-29 |  | US Foods format 2 feedback | [5 empty] | Closed
2024-09-03 |  | Web Portal Download / Upload / Button | [5 empty] | Closed
2024-09-12 |  | Vendor Dedup - London-California | [5 empty] | Closed
2024-09-17 | Rebates / Admin Fee | New Dataset London Q2 2024 | Vendor Deduping - 220 vendors - with next run + new vendors from new admin fee reports | Product Engineering |  |  |  | Pending
|  | US Foods - PO pdf vs PO file | [5 empty] | Closed
2024-08-26 |  | Website - fix link from Google | [5 empty] | Closed
2024-10-08 | Rebates / Admin Fee | Medline Item-Commodity | Exploring ways to automate | Product Engineering | Check web scrapping for Medline |  |  | Pending
2024-10-10 | Rebates / Admin Fee | Iteration-II Payment Terms & Rebate Terms | payment clause hold for delivery in Jan; rebates we expect 12/4 | Kristina | feedback provided 12/9/2024 | 2024-12-09 |  | Closed
2024-10-17 | General | Web Portal - Member Name hide | [5 empty] | Done
2024-10-17 | Rebates / Amin Fee | Medline Urology Review | done |  |  |  |  | Done
2024-11-05 | Discounts | Medline / Medtornic - match contract items to spend items to validate price applied | Mapping to spend descriptions in progress | Dr.Gen / Kristina | Categorization close to completion; next - lineage to spend (430 records completed) | 2024-12-12 |  | Pending
2024-10-22 | Payment Terms | Payment Terms in db | reports recreated using db tables. Supplier tier was connected as manual flag. | Sveta | feedback sent: add vendor_group_key into fact table. Use alias_name for relation | 2025-01-23 |  | Hold
2024-11-05 | Admin Fee | MPNs to AP line descriptions | explore enrichment | Dr.Gen |  |  |  | Closed
2024-11-05 | Invoice Anomalies | Duplicate Payments: Iteration-I | Sequence numbers added into 2023; wip for 2021-2022 | Daria | feedback provided 12/9/2024. Vineet & Sveta patterns | 2024-12-20 |  | Closed
2024-11-07 | US Foods Report | Client expects price variation insights |  | Product Engineering | commodities for the next 4 base products | December last 2 weeks |  | Closed
2024-11-07 | Admin Fee | File upload for London team | [5 empty] | Done
| GPO Admin Fees | AP-PO-Price File 2023 Urological Price File |  | Sveta | feedback sent 12/5/2024 | 2024-12-04 |  | Closed
| Contract Rebates (non-GPO) | AP-PO -Contract 16825 gloves |  | Sveta | feedback sent 12/5/2024 | 2024-12-04 |  | Closed
2024-11-26 | Invoice Anomalies | Payment Anomalies Iteration-I | relate to Satori cases | Kristina | feedback sent |  |  | Closed
2024-11-26 | Invoice Anomalies | Dates Anomalies Iteration-I |  | Kristina | feedback sent |  |  | Closed
2024-11-26 | Invoice Anomalies | Payment Terms Anomaly Iteration-I | payment made, after a gap | Kristina | feedback sent | 2024-12-03 |  | Closed
2024-12-12 | Development | Transaltion of PO file - Portugal |  |  | feedback sent |  |  | Closed
2024-12-12 | Development | Portugal PO File Categorization |  |  | feedback sent |  |  | Closed
2024-12-16 | Sequantix | Demo reports |  | Sveta | Demo files + List of people | 2024-12-20 |  | Closed
2024-12-16 | Rebates | Iteration-III Rebate Terms (clause and flag) | feedback provided 12/17/2024 | Hunter/Kristina | feedback sent 6/01 |  |  | Closed
2024-12-16 | Invoice Anomalies | London - California exports | received |  | no action required, files received | 2024-12-17 |  | Closed
2024-12-16 | Payment Terms | Iteration-III Payment Terms (days and text) |  | Kristina | feedback provided 21/01 | 2025-01-21 |  | Active
2025-01-13 | Invoice Anomalies | Duplicate Payments: Iteration-III (main model) | run on 2021-2023 combined | Daria | feedback provided 13/01 | 2025-01-13 |  | Active
2025-01-13 | Invoice Anomalies | Payment Anomalies Iteration-II (anomalies in amounts) |  | Daria | feedback provided 17/01 |  |  | Active
2025-01-13 | Invoice Anomalies | Payment Terms Anomaly Iteration-II (anomalies in payment after due date) |  | Semen |  |  |  | Pending
2025-01-13 | Portugal | Categorization iteration-I |  | Hunter / Kristina / Dr.Gen | pharm, med equipment & IT feedback provided | 2025-01-27 |  | Active
2025-01-13 | Sequantix Demo | Educational session | discuss demo structure, incporporate need of portal up request | Sveta / Hunter |  |  |  | Hold
2025-02-04 | Environment for CCHS | New: Setup direct environment for CCHS SOW | name + email ; file size <8 GB |  | Rohit to create a separate direct bucket for their data. Find data refresh file size to determine portal vs WinSCP. |  | 1 | Closed
2025-02-04 | Anomalies | Test Anomalies App | communicate test hours & conference hours |  | Provide access plus demo from Vineet on operation. Share of sample data |  |  | Closed
2025-01-22 | Anomalies | Automated reporting integrated to anomalies interface | awaiting to receive db reports to remove Confirmed views | Vineet / Babu | Create stage 1 slimmed down reporting upon first upload. Then create stage 2 reports after manual intervention by procurement for later iterated output. |  |  | Closed
2025-02-04 | Anomalies | Documentation for Q4 reports | 3 db reports; 2 flat files |  | Q3 reports need to be closed off for their production reporting. | 2025-02-12 |  | Closed
2025-01-13 | Portugal | SLU assignment |  | Daria / Dr. Gen | feedback provided 28/01 | 2025-01-29 |  | Active
2025-01-22 | Operations | Clean-Up | request placed to clean up Delete folder |  | No customer data should be kept past a certain period in individual folders. |  |  | Closed
2025-01-22 | Anomalies | 2021-2023 output |  | Daria / Kristina | 21-22 ML-based model wip; rest validated |  | 2 | Active
2025-02-20 | Anomalies | 2020 Output |  | Daria | 98% reviewed; transaction >$1.5k investigated |  | 1 | Active
2025-02-18 | Anomalies | 2020 Vendor Dedup |  | Daria / Kristina |  | 2025-02-18 |  | Closed
2025-02-25 | Anomalies | New confirmed instances - mutual process of knowledge update | [5 empty] | Closed
2025-02-25 | Anomalies | 2024 Vendor Dedup | [5 empty] | Closed
2025-02-20 | Anomalies | Vendor Master List Sync | 2020, 2024 deduping valdation complete. next steps? | Sveta / Daria / Vineet | Vineet to share the output (~300 vendors mismatch) |  |  | Active
2025-02-20 | Anomalies | 2024 Output |  | Daria | Fuzzy to be reviewed 27/02. ML1,ML2, rules ro be validated by 4/03 |  | 1 | Active